## Slide 1: Progress and plans of AUTH Presenter: Ioanna Chouvarda
2nd Project Meeting, 4-5 October 2018
Host: University of St. Kliment Ohridski – Bitola, FIKT (PB2)
Venue: Hotel Premier conference room, Stiv Naumov 12, 7000 Bitola

## Slide 2: Progress and current status: Overview
  Local management team was assigned
    I. Chouvarda
    Y. Karavidopoulou
  Key staff was hired
    One (1) Communication Manager (A. Mourouzis) – also involved in WP3, WP4 and WP5
    One (1) Chief developer (V. Kilintzis)
    One (1) Expert developer (N. Beredimas)
    Two more positions will be announced
  A tender for the Survey of D3.1.1 is under preparation
  A tender for the Educational material of D4.1.3 is under preparation

## Slide 3: Progress and current status in WP2
  D2.1.1 Dissemination strategy & monitoring:
    The CM will circulate a questionnaire for drafting the communication plan of the project
    All partners will need to spend some time and respond promptly
  D2.1.4 Project Website:
    A person is already assigned for content writing / management
    Basic project info will be circulated in order to be translated appropriately (by whom? PB2? Other?)

## Slide 4: Progress and current status in WP3
  D3.1.1 Joint study of needs and gaps:
    We are working on the relevant ToRs
  D3.1.2 Inspections and data collection:
    Start-up input is expected from PB3

## Slide 5: Progress and current status in WP4 & WP5
  D4.1.2 PHR for CB use:
    Our team is already working on the overall architecture and on the design of the PHR
    Two new s/w developers positions will also be announced soon
  D4.1.3 E-learning (health & digital health literacy):
    We are working on the relevant ToRs
  D5.1.1 Mobile sets for preventive health checks:
    Our team is already working on the design (devices, usage scenarios, requirements)
    Two new s/w developers positions will also be announced soon

## Slide 6: Progress and current status in WP6
Not opened yet
We are awaiting for joining the study visits preparations