## Slide 1: Progress and plans of PB3 - NCDP Presenter: Alexandros Mourouzis
2nd Project Meeting, 4-5 October 2018
Host: University of St. Kliment Ohridski – Bitola, FIKT (PB2)
Venue: Hotel Premier conference room, Stiv Naumov 12, 7000 Bitola

## Slide 2: Progress and current status per Deliverable
Overview:
  Staff assigned to the project
  External service subcontracted for local management support (13.024€)
  The original plan for three (3) separate tenders had to be abandoned, further to the clarifications received from the MA in the context of other Interreg projects of ESAmeA
  A new open procedure tender has been prepared with two lots:
    Special s/w development: 79.980€
    Consulting services (studies, training, …): 106.600€
  Upon approval it shall be launched. Expected for mid-end October

## Slide 3: Progress and current status per Deliverable
WP1
  1.3.2 Project management: Local project manager was assigned to the project
  1.3.3 Project meetings: Will host project meeting No3?
  1.3.4 External technical support: Preparation of procedure for selecting a subcontractor for project management support under D1.3.4
  Audits: Plan to file a very first costs verification request within 2018.

## Slide 4: Progress and current status per Deliverable
WP2: All dels are subcontracted (external)
  D2.3.2 Communication material & tools: shall be made available in January 19
  Public Project events: We specify the date from 1st Feb onwards
  Project website (WCAG 2.0, AA): a first version shall be up and running in mid January 19

## Slide 5: Progress and current status per Deliverable
WP3: All dels are subcontracted (external)
  D3.3.1 Joint study of needs and gaps
  D3.3.2 Inspections and data collection
  D3.3.3 Common strategy, action plan & guide: Who is leading the development of the joint strategy and action plan? Is it PB2 (staff)?
  D3.3.5 Awareness and activation raising campaign
  The first 3 activities are planned for the first 3-4 months of the contract
  The last activity will follow after

## Slide 6: Progress and current status per Deliverable
WP4: The del is subcontracted (external)
  D4.3.1 Cross-border Portal for accessible health services
WP5: The del is subcontracted (external)
  D5.3.3 Mobile app for citizens & medical tourists
  The subcontractor (of lot #2) is required to assign a technical manager who will be responsible for communicating with the LB1 and PB2 tech teams; will also join next skype and project meetings

## Slide 7: Progress and current status per Deliverable
WP6:
  D6.3.1 Pilot programme with Municipalities: The staff will be activated a couple months before the launch of the pilot
  D6.3.5 Study visits abroad: Any draft plan /schedule from the activity leader? Shall the partners propose destination? We may need to move the T&A to external

## Slide 8: Planned activities until M12
3rd Project meeting in Thessaloniki - Feb 2019?
Delivery of the project’s basic communication/dissemination kit - in early Jan, feedback on the drafts will be requested from all PBs
The Opening Conference in Thessaloniki - Feb 2019, jointly with the 3rd meeting?
Launch of the 1st online version of the Project website (WCAG 2.0, AA) - in late Dec /early Jan, feedback on the draft and preliminary content will be requested from all PBs
Most our WP3-WP4-WP5 activities shall be completed around June 2019