## Slide 1: 4th Project Meeting in Municipality of Ohrid Presenter: Gjorgji Trpeski
4th Project Meeting, {05-06} {September} {2019}
Host: Municipality (PB4)
Venue: Hotel Metropol - Ohrid

## Slide 2: Status of staff recruitments
  WP1
  Project Staff
  D1.4.2 Staff Costs Project manager 1 Person responsible (local Project Manager) for the management of the project (reporting, monitoring, etc.) - part time, 24 months
  D1.4.2 Staff Costs Financial manager 1 Person (Financial Manager) responsible for financial issues- part time, 24 months
  Organization of events
  WP2
  D2.4.3 Staff Costs Administrative staff 1 Person (Assistant) responsible for organizing the event
  WP3
  D3.4.2 External Expertise and Services Technical or scientific Expertise 1. Recruitment and payment of the inspectors (3 inspectors X 4 months X 550€). 2. Transportation and catering (4 months X 400€/month)
  D3.4.2 Staff Costs Technical Staff Person responsible for coordinating the inspections, making all preparatory communications, reporting, etc. Approx. 216 hrs within 5 months
  D3.4.4 Staff Costs Technical Staff Person responsible for organising the workshops (planning, communications, reporting, etc.)
  WP4
  D4.4.5 Staff Costs Technical Staff 1 Person responsible for the HelpDesk for vulnerable groups (6 months, 160hrs / month)
  WP6
  D6.4.1 Staff Costs Technical Staff Person responsible for coordinating the pilot programme in Ohrid. Approx. 240 hrs in 7 months
  D6.4.2 Staff Costs Technical Staff Person responsible for coordinating the mobile programme in Ohrid. Approx. 4 months X 72hrs/ month

## Slide 3: Status of Tenders
  WP1
  D1.4.3 External Expertise and Services Event organisation Organisation of 1 two-days meeting (coffee/beverages, meals for 20 people in each meeting). 1 Meeting X 2 days X 20 persons X 15€ per persons/ per day
  WP2
  D2.4.3 External Expertise and Services Event organisation Organisation of a one-day Public Project Event (Opening Project Conference). Snacks, coffees and beverages for 150 persons (150 X 6€) + sign language translation (30€/hr X 4hrs) + live broadcasting service (0,00€) + conference room & equipment (250€)
  WP3
  D3.4.1 External Expertise and Services Other Public opinion poll (questionnaire-based, through telephone survey) with 2000 people minimum
  D3.4.1 External Expertise and Services Other Translation costs (EN) for of the final report of the Public opinion poll (80 pages X 12€/page)
  D3.4.3 External Expertise and Services Other Publishing (printing) of the Joint Guide (see D4.3.3). EN (1000 items X 2,5euro / item), GR (2000 items X 2,5 euro/item), MK (2000 items X 2,5 euro / item)
  D3.4.4 External Expertise and Services Event organisation Organisation of 2 three-day workshops. Snacks, coffees etc. for 80 persons (80 X 5€ X 3 days) + room & equipment (150€ X 3 days )+ live broadcasting (0,00€/day) + notepads, pens, folders, etc. for 100 persons (100 X 0,75€)
  D3.4.4 External Expertise and Services Technical or scientific Expertise Payment to 3 adult trainers, to prepare the educational material and conduct 1 day training (1 day for each workshop)

## Slide 4: Status of Tenders
  WP4
  D4.4.5 Equipment Other specific equipment Supply, installation and maintenance service for 1 public (indoor) interactive workbench (4500€).
  WP5
  D5.4.1 Equipment Other specific equipment Provision, installation and maintenance of 3 complete sets of equipment (tablet, wireless sensors for vital sign recording (heart rate, heart pressure, spirometer, cardiograph, weight scale, body temperature, and arterial oxyhemoglobin saturation (Sp02), etc.)
  D5.4.2 Equipment Other specific equipment Provision, installation and maintenance of 7 complete sets of equipment (tablet/mobile, wireless multi sensor for vital sign recording (heart rate, heart pressure, breath rating, cardiograph, body temperature, glucometer, etc.)
  WP6
  D6.4.1 External Expertise and Services Technical or scientific Expertise Recruitment of experts team for the local center (2 nurse, 1 psychologist, 2 health visitor, 1 social worker, 1 data administrator). Estimated as follows: 7 professionals X 6 months of the Pilot programme in the Municipality X 500€/month in average.
  D6.4.2 External Expertise and Services Technical or scientific Expertise Recruitment of expert teams for the mobile units (2 health visitors, 2 social workers, data administrator,). Estimated as follows: 5 professionals X 3 months of the Mobile Units Programme X 600€ / month + travel costs (2350€).

## Slide 5: Status of Tenders
D6.4.2 Equipment Other specific equipment 1 urban vehicle X20100 eur = 20 100 eur . The vehicle shall be used for transport of the mobile units in the remote places for the pilot and mobile programme in Ohrid

## Slide 6: Implementation progress
  Current problems – Verification of Costs – transfer of funds

## Slide 7: Status of expenditures
  paid out so far 2000 EUR
  verified so far
  expected paid out expenditures so far – 30000 EUR

## Slide 8: Publicity outcomes and plans
  WP1
  D1.4.3 External Expertise and Services Event organisation Organisation of 1 two-days meeting (coffee/beverages, meals for 20 people in each meeting). 1 Meeting X 2 days X 20 persons X 15€ per persons/ per day
  WP2
  D2.4.3 External Expertise and Services Event organisation Organisation of a one-day Public Project Event (Opening Project Conference). Snacks, coffees and beverages for 150 persons (150 X 6€) + sign language translation (30€/hr X 4hrs) + live broadcasting service (0,00€) + conference room & equipment (250€)